Duration Estimate
Gant Chart

MealMind

4601 Mid Rivers Mall Drive

Cottleville, missouri, 63304

July 05, 2025

Table with Explanations:

| Durations Estimate |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project: MealMind |  |  |  |  | Date: 07/07/2025 |  |
| Activity | Resource(s) | Optimistic | Most Likely | Pessimistic | Estimated Activity Duration | Reserve |
| Color Scheme / Logo Finalization | All Team Members | 18 | 23 | 28 | 23.0 | 5.0 |
| Front-End Development Part 1 | Front-End Devs | 12 | 18 | 24 | 18.0 | 6.0 |
| Phase 2 Presentation | All Team Members | 1 | 2 | 3 | 18.0 | 1.0 |
| Back-End Development Part 1 | Back-End Devs | 25 | 31 | 37 | 31.0 | 6.0 |
| API Integration | Full Stack Dev | 8 | 11 | 15 | 11.0 | 4.0 |
| AI Recipe Curation | All Team Members | 10 | 15 | 20 | 15.0 | 5.0 |
| User Testing Round 1 | All Team Members | 3 | 5 | 7 | 5.0 | 2.0 |
| Back-End Dev Finalization | Back-End Devs | 30 | 36 | 42 | 36.0 | 6.0 |
| Front-End Dev Finalization | All Team Members | 30 | 36 | 42 | 36.0 | 6.0 |
| Feedback Review | All Team Members | 2 | 3 | 5 | 3.2 | 1.8 |
| Bug Fixes & Tweaks | Dev Team | 3 | 4 | 6 | 4.2 | 1.8 |
| Final Presentation | All Team Members | 3 | 4 | 6 | 4.2 | 1.8 |
| Project Completion | All Team Members | 45 | 51 | 57 | 51.0 | 6.0 |

*All calculations made using the PERT formula.

This free Duration Estimate Template is brought to you by www.ProjectManagementDocs.com